Risk register – August 2018

| ID | Risk | Date risk added | Owner | Level of risk without mitigation |  |  | Mitigation actions Impact | Level or risk with mitigation |  | Date risk closed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Likelihood (L, M, H) | Impact |  |  | Likelihood (L, M, H) | Impact |  |
| 1 | Insufficient data leading to delay | 03.07.17 | RHDHV | Medium | Delays to the programme until sufficient data is sourced. |  | Review of existing data and data request at start of project. Rapid and clear communication from RHDHV to EDDC. | Low | Delays in the programme. | 08/05/2018 |
| 2 | Time taken to calibrate models underestimated | 03.07.17 | RHDHV | Medium |  | Delays in the programme. | Initial assessment made on duration and float allowances made within programme activities. | Low | Delays in the programme. | 10/04/2018 |
| 3 | Accuracy of joint probability analysis challenged by EA | 03.07.17 | RHDHV | Low |  | Delays in the programme. | Joint probability analysis undertaken in line with Defra / EA desk based methodology (2005). | Low | Delays in the programme. | 08/11/2017 |
| 4 | Errors made in flood damage calculations. | 03.07.17 | RHDHV | Low |  | Delays in the programme. | Internal quality assurance checks. Transparent calculations from our Flood Risk Economic Damages tool to reduce risk. | Low | Delays in the programme. | 07/08/18 |
| 5 | Buried services and UXO impact on outline design. | 03.07.17 | RHDHV | Low |  | Design changes | Line search enquiry and high level UXO desk study undertaken during design. | Low | Design changes | 03/07/2018 |
| 6 | Option costs exceed previous estimates | 03.07.17 | RHDHV | Medium |  | Preferred option may not be feasible. Additional contributions may be required. | Early Supplier Engagement programmed early in programme to give project certainty and undertaken during option development phase. Rapid and clear communication from RHDHV to EDDC. Initial cost estimate considered earlier in programme in phase 1. | Low | Delays in the programme. |  |
| 7 | EIA scope is not broad enough resulting in delays | 03.07.17 | RHDHV | Low |  | Delays in the programme. | Early consultation with regulators to fix scope of EIA. RHDHV to communicate with regulators throughout. | Low | Delays in the programme. | 08/11/2017 |
| 8 | Outline business case is insufficient | 03.07.17 | RHDHV | Low |  | Delays in the programme. | Robust internal review process. Rapid and clear communication from RHDHV to EDDC. | Low | Delays in the programme. |  |
| 9 | Scheme budget underestimated | 03.07.17 | RHDHV | Medium |  | Delays in the programme. Funding may not be possible. | Input through Early Supplier Engagement and monte carlo analysis to assess risk. Rapid and clear communication from RHDHV to EDDC. | Low | Delays in the programme. |  |
| 10 | Cost certainty | 03.07.17 | RHDHV | Medium |  | Scheme may not be feasible. | Develop design using 3D model. Optimise design through Early Supplier Engagement. | Low | Delays in the programme. |  |
| 11 | Outputs from modelling are inconclusive to inform outline design | 03.07.17 | RHDHV | Medium |  | Delays in programme. | Revised modelling scope to help mitigate risk. Close attention and analysis throughout every stage. Rapid and clear communication from RHDHV to EDDC. | Low | Delays in the programme. | 07/08/18 |
| 12 | Adverse reaction from the general public | 03.07.17 | RHDHV | High |  | Delays in programme. | Consultation undertaken at key stages in the project. Regular communication updates. Develop communications plan. Use of a consultation engagement / feedback log. | Low | Delays in the programme. |  |
| 13 | Potential shortfall in FDGiA funding in financial years 19/20 and 20/21. | 14.11.17 | EDDC | Medium |  | Delays in programme. | Communication with EA to clarify funding availability. Review the overall programme and ensure that stakeholders are aware of the risk. | Medium | Delays in programme. | 07.12.2017 |
| 14 | Potential shortfall in large mass rock armour supply from Norway. | 07.12.2017 | EDDC | Medium |  | Delays in construction programme and potential increase in construction costs. | ECI contractor to provide updated advice on this in Phase 2. | Medium. | Delays in construction programme and potential increase in construction costs. |  |
| 15 | Risk of a potential buried service on East Beach as a potential service has been visible at very low tides. | 07.12.2017 | EDDC | Medium |  | Delays on site, increase in construction cost. | Undertake comprehensive desk based services search during outline design phase. | Low | Delays on site, increase in construction cost. | 03/07/2018 |
| 16 | Pedestrian access along East Beach could be cut off during a high tide due to the presence of a groyne structure putting the public at risk of being hit by falling cliff material. | 14.03.2017 | EDDC | Medium |  | Public health and safety | To be considered further during Outline Design. | Low | Public health and safety |  |
| 17 | Screening and scoping may change the planned scope of the EIA. | 15.03.2018 | EDDC | Low |  | Programme delay and potential increase in cost. | Liaison with LPA and MMO. | Low | Programme delay and potential increase in cost. | 03/07/2018 |
| 18 | Introduction of splashwall to the scheme may increase overall project cost and have an adverse reaction from the public over loss of views. | 15.03.2018 | EDDC | Medium |  | Programme delay and potential increase in cost. | Liaison with public during exhibition. Assessment as part of LVIA. Make allowance for aesthetically pleasing wall design. | Medium | Programme delay and potential increase in cost. |  |